ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	1

1.1.	Beneficiary country	1

1.2.	Contracting Authority	1

1.3.	Relevant country background	1

1.4.	Current state of affairs in the relevant sector	1

2.	CONTRACT PURPOSE & EXPECTED RESULTS	1

2.1.	Overall objective	1

2.2.	Purpose	1

2.3.	Results to be achieved by the Consultant	1

3.	ASSUMPTIONS & RISKS	1

3.1.	Assumptions underlying the project intervention	1

3.2.	Risks	2

4.	SCOPE OF THE WORK	2

4.1.	General	2

4.2.	Specific activities	2

4.3.	Project management	2

5.	LOGISTICS AND TIMING	2

5.1.	Location	2

5.2.	Commencement date & Period of execution	2

6.	REQUIREMENTS	3

6.1.	Personnel	3

6.2.	Office accommodation	3

6.3.	Facilities to be provided by the Consultant	3

6.4.	Equipment	3

7.	REPORTS	3

7.1.	Reporting requirements	3

8.	MONITORING AND EVALUATION	3

8.1.	Definition of indicators	3

# BACKGROUND INFORMATION

## Beneficiary country

Republic of Serbia

## Contracting Authority

Republic Hydrometeorological Service of Serbia

Kneza Viseslava 66,

11000 Beograd, Srbija

## Relevant country background

The project is organically suited to comprehensive targets of INTERREG program for the assisting of partnership of cross-border territories. The project willfulfill by taking into widespread of experts from both sides of the borders, the Hungarian and Serbian organizations and experts in closed partnership, the initiation of aspect of cross-border, the phasing of the ideas of the given point’s cooperation strategy and developing which are enhanced by the local and regional’s partnership networks. The aim of the project is to support cross-border cooperation in the environment protection and flood prevention.

## Current state of affairs in the relevant sector

Republic of Serbia is in the process of transition. Economic and social situation in the country are improving, but the level of economic development is not adequate for becoming EU candidate. Public utilities, environment monitoring, protection and flood prevention infrastructure need to be improved within project financed of municipal and republic budget and in cooperation with EU funds.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

- Quality and timely implementation of the project “Upgrading of monitoring system for the assistance of the environment protection and flood prevention in Vojvodina" - 04SER01/11/061, financed under the Neighbourhood Programme of the EU.

## Purpose

The purpose of this contract is as follows:

- Implementation of auditing of the project and provision of the auditing certificate.

## Results to be achieved by the Consultant

The results of the project will be in line with detailed presentation in the Annex 2 to this Terms of Reference.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project intervention

Not applicable.

## Risks

Not applicable.

# SCOPE OF THE WORK

## General

### Project description

The project will follow the provisions described in details in the Annex 2 to this Terms of Reference.

### Geographical area to be covered

Republic of Serbia, Region of Vojvodina and Belgrade

## Specific activities

The activities will follow the provisions describe in details in the Annex 2 to this Terms of Reference.

## Project management

### Responsible body

Republic Hydrometeorological Service of Serbia

Kneza Viseslava  66, 11000 Belgrade

Project Manager – Slavimir Stevanovic

### Management structure

# LOGISTICS AND TIMING

## Location

In Serbia.

## Commencement date & Period of execution

The intended commencement date is 28.04.2008. and the period of execution of the contract will be 30 days from this date.

# REQUIREMENTS

## Personnel

### Key experts

The contractor will provide sufficient staff for timely and quality implementation of the tasks described in the Annex 2 to this Terms of Reference.

The staff involved in the project will correspond to the requirements in line with certifying standards for the sector (i.e. will have adequate certification and authority to issue an auditing certificate).

### Support staff & backstopping

The contractor will provide sufficient support facilities, including transport means, for quality and timely implementation of the tasks described in the Annex 2 to this Terms of Reference. The costs of the supporting facilities will be borne by the contractor and will be included in the global price.

## Office accommodation

The tasks will be implemented in locations of the project and at the home office of the contractor. The costs of the office will be borne by the contractor and will be included in the global price.

## Facilities to be provided by the Consultant

The contractor will provide sufficient support facilities, including transport means, for quality and timely implementation of the tasks described in the Annex 2 to this Terms of Reference. The costs of the supporting facilities will be borne by the contractor and will be included in the global-price.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority.

# REPORTS

## Reporting requirements

No special reporting is anticipated in the project. The project will be measured upon the deliveries mentioned in the Annex 2 to this Terms of Reference (audit certificate and auditing report).

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the project is ‘’audit certificate and auditing report delivered as mentioned in the Annex 2’’.

## Information about the Subject of Expenditure Verification

| Information about the Subject of the Expenditure Verification |  |
| --- | --- |
| Reference number and date of the Grant Contract | 04SER01/11/061, in Novi Sad 19/05/2006 |
| Grant contract title | Upgrading of monitoring system for the assistance of the environment protection and flood prevention in Vojvodina" |
| Country | Republic of Serbia |
| Beneficiary | Republic Hidrometeorological Service |
| Budget line Grant Contract | / |
| Legal basis for the Grant Contract | General agreement between FRY and EU |
| Start date of the Action | 19.05.2006. |
| End date of the Action | 15.05.2008. |
| Total cost of the Action | 296.000,00 Euro |
| Grant maximum amount | 270.000,00 Euro |
| Total amount received to date by the Beneficiary from Contracting Authority | 216.000,00 |
| Total amount of the payment request |  |
| Contracting Authority | European Agency for Reconstruction, Vasina 2-4, 11000 Beograd |
| European Commission | - |
| Auditor |  |

## Annex 2: Scope of Work – Procedures to be performed

The Auditor designs and carries out his verification work programme in accordance with the objective and scope of this engagement and the procedures to be performed as specified below. When performing these procedures the Auditor may apply techniques such as inquiry and analysis, (re)computation, comparison, other clerical accuracy checks, observation, inspection of records and documents, inspection of assets and obtaining confirmations.

The Auditor obtains sufficient appropriate verification evidence from these procedures to be able to draw up a report of factual findings. For this purpose the Auditor can refer to the guidance provided by International Standard on Auditing 500 “Audit Evidence” and in particular by the paragraphs relating to ‘sufficient appropriate audit evidence’. The Auditor exercises professional judgment as to what is sufficient appropriate verification evidence where he believes that the guidance provided by ISA 500, the terms and conditions of the Grant Contract and the ToR for this engagement are not sufficient.

The General Conditions of the Grant Contract (‘General Conditions’) and notably Article 16.3 thereof provide an indicative list of the types and nature of evidence that the Auditor may often find in expenditure verifications. This may vary depending on the nature of the expenditure and the practices in the country concerned.

1	Obtaining a sufficient Understanding of the Action and of the Terms and Conditions of the Grant Contract

The Auditor obtains a sufficient understanding of the terms and conditions of the Grant Contract by reviewing the Grant Contract and its annexes and other relevant information, and by inquiry of the Beneficiary. The Auditor ensures that he obtains a copy of the original Grant Contract (signed by the Beneficiary and the Contracting Authority) with its annexes. The Auditor obtains and reviews copies of the Final Narrative Report.

The Auditor pays particular attention to Annex I of the Grant Contract, which contains the Description of the Action, Annex II (General Conditions) and Annex IV, which provides rules for procurement (including nationality and origin rules) by grant beneficiaries in the context of EC external actions.  Failure to comply with these rules makes expenditure ineligible for Community financing. These procurement rules apply to all grant contracts but depending on the legal basis for the grant contract (for example TACIS, ALA and Food Aid) nationality and origin rules may vary. The Auditor should ensure with the Beneficiary that the applicable nationality and origin rules are identified and understood. Applicable rules of nationality and origin are set out, for each legal basis, in Annex A2 to the Practical Guide to contract procedures for external actions of the European Communities. If the Auditor finds that the terms and conditions to be verified are not sufficiently clear he should request clarification from the Beneficiary.

2	Procedures to verify the Eligibility of Expenditure Claimed by the Beneficiary in the Financial Report for the Action

2.1	General Procedures

2.1.1	The Auditor verifies that the Financial Report complies with the conditions of the Grant Contract notably with Article 2 of the General Conditions (including format and language).

2.1.2	The Auditor examines whether the Beneficiary has complied with the rules for accounting and record keeping of the Grant Contract notably with Article 16 of the General Conditions. The purpose of this is:

-	To assess whether an efficient and effective expenditure verification of the Financial Report is feasible; and

-	To report important exceptions and weaknesses with regard to accounting, record keeping and documentation requirements so that the Beneficiary can undertake follow-up measures for correction and improvement for the remaining implementation period of the Action.

2.1.3	The Auditor reconciles the information in the Financial Report to the Beneficiary’s accounting system and records (e.g. trial balance, general ledger accounts, sub ledgers etc.).

2.1.4	The Auditor verifies that the correct exchange rates have been applied for currency conversions where applicable and in accordance with the conditions of the Grant Contract notably Article 15.9 of the General Conditions.

2.2	Conformity of Expenditure with the Budget and Analytical Review

The Auditor carries out an analytical review of the expenditure headings in the Financial Report and:

-	verifies that the budget in the Financial Report corresponds with the Budget of the Grant Contract (authenticity and authorisation of the initial Budget) and that the expenditure incurred was foreseen in the budget of the Grant Contract.

-	verifies that the total amount claimed for payment by the Beneficiary does not exceed the maximum grant laid down in Article 3.2 of the Special Conditions of the Grant Contract.

-	verifies that any amendments to the Budget of the Grant Contract comply with the conditions for such amendments (including where applicable the requirement for an addendum to the Grant Contract) as set out in Article 9 of the General Conditions.

-	verifies that the conditions for profit in Article 17.3 of the General Conditions were respected.

2.3	Selecting Expenditure for Verification

2.3.1	Expenditure Headings, Subheadings and Items

The expenditure claimed by the Beneficiary in the Financial Report is presented under the following expenditure headings: 1 Human Resources, 2 Travel, 3 Equipment and Supplies, 4 Local office, 5 Other costs, services, 6 Other and 8 Administrative costs. Expenditure headings can be broken down into expenditure subheadings such as for example 1.1 Salaries.

Expenditure subheadings can in principle be broken down into individual expenditure items or classes of expenditure items with the same or similar characteristics. The form and nature of the supporting evidence (e.g. a payment, a contract, an invoice etc) and the way expenditure is recorded (i.e. journal entries) vary with the type and nature of the expenditure and the underlying actions or transactions. However, in all cases expenditure items reflect the accounting (or financial) value of underlying actions or transactions no matter the type and nature of the action or transaction concerned.

2.3.2	Selecting Expenditure Items

Value should be the primary factor used by the Auditor to select expenditure items or classes of expenditure items for verification. The Auditor selects high value expenditure items to ensure an appropriate coverage of expenditure.

Moreover, the Auditor uses his judgment to select specific expenditure items or classes of expenditure items. The Auditor may use factors such as his knowledge of the action and the characteristics of the expenditure categories, classes and items being verified such as for example expenditure items that are unusual or inherently risky or error prone.

2.4	Verification of Expenditure

The Auditor verifies the expenditure and reports all the exceptions resulting from this verification. Verification exceptions are all verification deviations found when performing the procedures set out in this Annex. In all cases the Auditor assesses the (estimated) financial impact of exceptions in terms of ineligible expenditure. For example: if the Auditor finds an exception with regard to procurement rules he assesses to which extent this exception has led to ineligible expenditure. The Auditor reports all exceptions found including the ones of which he cannot measure the financial impact. Having selected the expenditure items the Auditor verifies them by testing for the criteria set out below.

2.4.1		Eligibility of Direct Costs

The Auditor verifies the eligibility of direct costs with the terms and conditions of the Grant Contract notably Article 14 of the General Conditions. He verifies that these costs:

-	are necessary for carrying out the action. In other words the Auditor verifies that expenditure for a transaction or action has been incurred for the intended purpose of the action and that is has been necessary for the activities and objectives of the action. The Auditor further verifies that the direct costs are provided for in the Grant Contract Budget and comply with the principles of sound financial management, in particular value for money and cost effectiveness;

-	have actually been incurred by the Beneficiary or his partners during the implementation period of the Action as defined in Article 14.1 of the General Conditions;

-	are recorded in the accounts of the Beneficiary and are identifiable, verifiable and substantiated by originals of supporting evidence.

The Auditor also considers non-eligible costs as described in Article 14.3 of the General Conditions. In this respect the Auditor verifies in particular whether expenditure includes certain taxes, including VAT. If this is the case the Auditor verifies whether the Beneficiary (or, where applicable the partners) cannot reclaim these taxes and whether the applicable regulations, rules and practices in the country concerned allow the coverage of these taxes in the expenditure. Copies of all relevant documents for this shall be attached to the Report.

2.4.2	Accuracy and Recording

The Auditor verifies that expenditure for a transaction or action has been accurately and properly recorded in the Beneficiary’s accounting system and the Financial Report and that it is supported by appropriate evidence and supporting documents. This includes proper valuation and the use of correct exchange rates.

2.4.3	Classification

The Auditor verifies that expenditure for a transaction or action has been classified under the correct heading and subheading of the Financial Report.

2.4.4	Reality (occurrence / existence)

The Auditor exercises professional judgment to obtain sufficient appropriate verification evidence as to whether the expenditure has occurred (reality and quality of the expenditure) and - where applicable - assets exist. The Auditor verifies the reality and quality of the expenditure for a transaction or action by examining proof of work done, goods received or services rendered on a timely basis, at acceptable and agreed quality and at reasonable prices or costs. The list of assets physically checked shall be attached to the Report.

2.4.5	Compliance with Procurement, Nationality and Origin Rules

The Auditor examines which procurement, nationality and origin rules apply for a certain expenditure heading, subheading, a class of expenditure items or an expenditure item. The Auditor verifies whether the Beneficiary has complied with such rules and whether the expenditure concerned is eligible. Where the Auditor finds issues of non-compliance with procurement rules, he reports the nature of such events as well as their financial impact in terms of ineligible expenditure.

2.4.6	Administrative (indirect) costs

The Auditor verifies that the administrative (indirect) costs (heading 8 of the Financial Report) do not exceed a maximum of 7% of the total direct eligible costs of the action (Article 14.4 of the General Conditions).

2.5	Verification Coverage of Expenditure

The Auditor applies the principles and criteria set out below when planning and performing the procedures for expenditure verification of Sections 2.3 and 2.4 above. This allows the Auditor to rationalise his verification work.

Verification by the Auditor and verification coverage of expenditure items does not necessarily mean a complete and exhaustive verification of all the expenditure items that are included in a specific expenditure heading or subheading. The Auditor should ensure a systematic and representative verification but depending on certain conditions (see further below) the Auditor may obtain satisfactory verification results for an expenditure heading or subheading by looking at a limited number of selected expenditure items. The list of expenditures verified shall be attached to the Report.

The Auditor may apply statistical sampling techniques for the verification of one or more expenditure headings or subheadings of the Financial Report. For this purpose the Auditor examines whether the ‘populations’ (i.e. expenditure subheading or classes of expenditure items within an expenditure subheading) are suitable and sufficiently large (i.e. they should be made up of a large amount of items) for effective statistical sampling. This enables the Auditor to obtain and evaluate verification evidence to form a conclusion on the total of the population from which the sample is drawn. The Auditor may refer to IFAC International Standard on Auditing 530 ‘Audit sampling and other selective testing procedures’ for guidance.

2.5.1	Expenditure Coverage Ratio (‘ECR’)

The Expenditure Coverage Ratio (‘ECR’) represents the total amount of expenditure verified by the Auditor expressed as a percentage of the total amount of expenditure reported by the Beneficiary in the Financial Report and claimed by the Beneficiary for deduction from the total sum of pre-financing under the Grant Contract. This amount is reported in Annex V of the Grant Contract. The Auditor ensures that the overall ECR is at least 65%. The Auditor selects expenditure items (see Section 2.3.2). If he finds an exception rate of less than 10% of the total amount of expenditure verified (i.e. 6,5 %) the Auditor finalises verification procedures and continues with reporting. If the exception rate found is higher than 10% the Auditor extends verification procedures until the ECR is at least 85%. The Auditor then finalises verification procedures and continues with reporting regardless of the total exception rate found.

The Auditor ensures that the ECR for each expenditure heading and subheading in the Financial Report is at least 10%.

2.6	Verification of Revenues of the Action

The Auditor verifies that revenues (including inter alia grants and funding received from other donors and revenue generated by the Beneficiary in the context of the action) have been appropriately allocated to the action subject of the Grant Contract and correctly disclosed in the Financial Report. As this engagement is not an audit the Auditor is not requested to assess the completeness of revenues.

# Report of Factual Findings for an Expenditure Verification of an EC financed Grant Contract for External Actions

To be printed on letterhead paper of the Auditor

<Name of contact person(s)>, < Position>

< Beneficiary’s name>

<Address>

<dd Month yyyy>

Dear <Name of contact person(s)>

In accordance with our contract dated <dd Month yyyy> with <name of the Beneficiary> “the Beneficiary” and the terms of reference attached thereto (Annex 1 of this report), we provide our Report of Factual Findings (“the Report”), with respect to the accompanying Financial Report you provided for the period covering <dd Month yyyy - dd Month yyyy> (Annex 2 of the Report). You requested certain procedures to be carried out in connection with the Grant Contract concerning [title and number of the contract], the ‘Grant Contract’. The Report consists of this letter and the Report details set out in Chapters 1 and 2.

Objective

Our engagement was an engagement to perform agreed-upon procedures regarding the expenditure verification of the grant contract between you and < the European Agency for Reconstruction > the ‘Contracting Authority’. It involved performing certain specified procedures, the results of which the Contracting Authority uses to draw conclusions from the procedures performed by us.

The objective of this expenditure verification is for the Auditor to verify that the expenditure claimed by the Beneficiary in the Financial Report for the action financed by the Grant Contract has occurred (‘reality’), is accurate (‘exact’) and eligible and to submit to the Beneficiary the Report with regard to the agreed-upon procedures performed . Eligibility means that the funds provided by the grant were spent in accordance with the terms and conditions of the Grant Contract.

Scope of Work

Our engagement was undertaken in accordance with:

-	the terms of reference in Annex 1 to this Report and:

-	International Standard on Related Services (‘ISRS’) 4400 Engagements to perform Agreed-upon Procedures regarding Financial Information as promulgated by the International Federation of Accountants (‘IFAC);

-	the Code of Ethics for Professional Accountants issued by the IFAC. Although ISRS 4400 provides that independence is not a requirement for agreed-upon procedures engagements, the Contracting Authority requires that the auditor also complies with the independence requirements of the Code of Ethics for Professional Accountants;

As requested, we have only performed the procedures set out in the terms of reference for this engagement and we have reported our factual findings on those procedures in Chapter 3 of this Report.

The scope of these agreed upon procedures has been determined solely by the Contracting Authority and the procedures were performed solely to assist the Contracting Authority in evaluating whether the expenditure claimed by the Beneficiary in the accompanying Financial Report has occurred (‘reality’), is accurate (‘exact’) and eligible.

Because the procedures performed by us did not constitute either an audit or a review made in accordance with International Standards on Auditing or International Standards on Review Engagements, we do not express any assurance on the accompanying Financial Report.

Had we performed additional procedures or had we performed an audit or review of the financial statements of the Beneficiary in accordance with International Standards on Auditing, other matters might have come to our attention that would have been reported to you.

Sources of Information

The Report sets out information provided to us by the management of the Beneficiary in response to specific questions or as obtained and extracted from the Beneficiary’s information and accounting systems. In addition we received verbal representations from the Beneficiary’s management which we did not obtain in writing [delete if received in written form.]

Factual Findings

The total expenditure which is the subject of this expenditure verification amounts to <xxxxxx> €.

The Expenditure Coverage Ratio is <xx%>. This ratio represents the total amount of expenditure verified by us expressed as a percentage of the total expenditure which has been subject of this expenditure verification. The latter amount is equal to the total amount of expenditure reported by the Beneficiary in the Financial Report (Annex 2) and claimed by the Beneficiary for deduction from the total sum of prefinancing under the Grant Contract as per the beneficiary’s Request for Payment of <dd Month yyyy>.

Based on the agreed-upon procedures that we performed we found that expenditure amounting to <xxxx> € is not eligible. The details of our factual findings including a summary table of the expenditure that is not eligible are presented in Chapter 2 of this Report.

Use of this Report

This Report is solely for the purpose set forth in the above objective.

This report is prepared solely for the confidential use of the Beneficiary and the Contracting Authority and solely for the purpose of submission to the Contracting Authority in connection with the requirements as set out in Article 15 of the General Conditions of the Grant Contract. This report may not be relied upon by the Beneficiary or by the Contracting Authority for any other purpose, nor may it be distributed to any other parties. The Contracting Authority may only disclose this Report to others who have regulatory rights of access to it in particular the European Commission, the European Anti Fraud Office and the European Court of Auditors.

This Report relates only to the Financial Report specified above and does not extend to any financial statements of the Beneficiary.

We look forward to discussing our Report with you and would be pleased to provide any further information or assistance which may be required.

Yours sincerely

<dd Month yyyy>

<Name of the Auditor>

Report Details

Chapter 1	Information about the Grant Contract and the Action

[Chapter 1 should include a description of the Action concerned and the Grant Contract, the beneficiary/ implementing structure and key financial/budget information. The Auditor should also present here the table with ‘Information about the subject of the Expenditure Verification’ as attached by the Beneficiary to the ToR .The information in this table should be verified by the Auditor]

Chapter 2	Procedures Performed and Factual Findings

We have performed the procedures as agreed upon in the terms of reference for an expenditure verification of the Grant Contract concerning < title and number of the action/contract> (see Annex 1). The factual findings of these procedures are set out under the headings below.

[Describe the results of procedures performed. Use supporting schedules as Appendices to the Report, if applicable.]

[Insert (if any): Details of exceptions:……]

1	Obtaining a sufficient Understanding of the Action and of the terms and conditions of the Grant Contract

2	Procedures to verify the Eligibility of Expenditure claimed by the Beneficiary in the Financial Report for the Action

2.1	General Procedures

2.2	Conformity of Expenditure with the Budget and Analytical Review

2.3	Selecting Expenditure for Verification

2.4	Verification of Expenditure

2.4.1	Eligibility of Direct Costs

2.4.2	Accuracy and recording

2.4.	3.	Classification

2.4.4	Reality (Occurrence / existence)

2.4.5	Compliance with procurement, nationality and origin rules

2.4.6	Administrative (indirect) costs

2.5		Verification Coverage of Expenditure

2.5.1	Expenditure Coverage Ratio (‘ECR’).

2.5.2	Sufficient spread of the ECR over expenditure categories.

2.6		Verification of Revenues of the Action

Annex 1	Terms of Reference

Annex 2	Financial Report as provided by the Beneficiary

See http://europa.eu.int/comm/europeaid/tender/gestion/index_en.htm